## Sheet1
Screen Name: General
Task | Assigned to | Status
Creating fragments and linking to activities so that the title of the app changes based on the current active screen | Sarmad
Identify the ways to show notification | Manasa | In-progress
Creating screens for capturing user profile details |  | To be picked at last
Screen Name: Groceries
Task | Assigned to | Status
Creating add button in the grocery screen and make it available only for grocery screen | Sarmad | Completed
API for Groceries: Add, Edit, Delete, Search grocery | Abinaya | Completed
Open Camera on click of "Add" in grocery screen
On close of camera view, open the "Add Grocery" screen
Add Grocery screen and insert the data into database | Sarmad | In-progress
Merge Grocery list view POC into master
Open Edit Grocery on Click of Edit button from list view and update the changes into the database
Delete grocery from list
Confirmation before deleting grocery from list
Highlighting the items "about to expire" in the groceries list view
Show notification to remove the expired item from list
Screen Name: Recipes
Task | Assigned to | Status
Create API for generating suggested recipes based on the available recipes
API for retrieving recipe detail
Retrieving image for recipe from API
Integrating Recipe card view into master | Abinaya | Completed
Creating recipe detail view page
Redirecting to recipe detail view on click of a recipe
Screen Name: Activity
Task | Assigned to | Status
Creating UI for activity with progress chart | Jesse | In-progress
Integrating activity POC into master | Jesse